Campaign Timeline Example

Note: This is an example of timeline from the final days of an election campaign for parliament with open party lists.

| DATE | ACTIVITY | RESPONSIBLE | RESOURCES |
| --- | --- | --- | --- |
| After E-Day | Finalize all tasks, pay workers | Campaign Manager, Office Manager, Finance Director | Money |
| Election Day | GOTV – door-to-door | -Campaign Manager/Field Director – identify target areas -Database Manager – produce lists of target voters -Volunteer Coordinator – recruit volunteers to prepare GOTV materials and conduct GOTV | GOTV leaflet Script for volunteers Lists of target voters or areas Maps of areas to be covered 200 Volunteers |
|  | GOTV – phone calls and SMS | -Campaign Manager and Field Director – identify target calls and write script -Database Manager – produce lists of target voters -Volunteer Coordinator – recruit volunteers | Script for phone calls Call lists 80 Volunteers (on a rotation) |
|  | Observation at polls and vote count | -Campaign Manager and Field Director – identify key polls and counting centers -Volunteer Coordinator – recruit and train volunteers | Observation check list 50 Volunteers |
|  | Candidate Press Events | -Campaign Manager and Press Officer – define press strategy for the day and arrange press events -Candidate | Press packets Election day speech for candidate |
| Election Day minus 1 | Voter Contact – door-to-door in last 1/3 of B and C areas | Field Director and Volunteer Coordinator | Persuasion leaflet 150 Volunteers |
|  | Candidate Visits to key community leaders to solidify their endorsements | Candidate and Campaign Manager | Small thank you gifts for leaders |
|  | Candidate Press Events | Candidate and Press Officer | Press packets Speech for candidate |
| Election Day minus 2 | Voter Contact – door-to-door in middle 1/3 of B and C areas | -Campaign Manager/Field Director – identify areas -Database Manager – produce lists of target voters -Volunteer Coordinator – recruit volunteers to conduct door-to-door | Door-to-door leaflet Script for volunteers Lists of target voters and maps Voter contact cards 100 Volunteers |
|  | Rally in town center – large event to mobilize A voters and supporters and raise candidate profile coming up to election day | Campaign Manager Field Director Volunteer Coordinator Press Officer Candidate | Notices/invitations to supporters Banner and podium sign for stage Balloons, bunting, decorations Band or music Speech for candidates |
|  | Outreach Tents – set up tents in key areas and invite local residents to come and meet the candidate; offer refreshments/hospitality | Field Director Volunteer Coordinator Candidate | Mobile tent Campaign literature Voter contact cards Sweets and drinks 10 Volunteers |
| Election Day minus 3 | Voter Contact – door-to-door in first 1/3 of B and C areas | -Campaign Manager and Field Director – identify target areas -Database Manager – produce lists of target voters -Volunteer Coordinator – recruit volunteers to conduct door-to-door | Door-to-door leaflet Script for volunteers Lists of target voters or areas Maps of areas to be canvassed Voter contact cards Stickers with campaign logo 100 Volunteers |
|  | Outreach Tents | Campaign Manager and Field Director – identify key areas to set up outreach tents Volunteer Coordinator – recruit volunteers to assist Candidate | Mobile tent Campaign literature Voter contact cards Sweets and drinks 10 Volunteers |
|  | Candidate Press Events | Press Officer – organize all press events Candidate | Press packets Talking points for candidate |
| Election Day minus 4 | Newspaper Ads – print final newspaper ads before election day targeting B and C voters | Campaign Manager and Candidate – shape message for advertisements Press Officer – Shape message and organizes the ads | Money |
|  | Facebook Campaign – use to begin to mobilize supporters to vote | New Media Officer and Press Officer | Computers |
| Election Day minus 5 | Voter Contact – mailing to B and C voters | -Campaign Manager and Field Director – identify target areas or voters -Database Manager – produce contact lists -Volunteer Coordinator – recruit volunteers | Letter or leaflet Contact lists Envelopes and stamps 50 Volunteers |
|  | Fundraising Event – gala evening at home of strong supporter | Fundraiser – organize event and recruit potential donors Candidate | Campaign literature Small thank you gift for host |

Adapted from NDI's Regional Campaign School Middle East and North Africa Module #9: Campaign Planning