Introduction to Monitoring and Evaluation

Objectives

- To understand the importance of monitoring and evaluation, key concepts and frameworks

- To consider how gender can be incorporated into monitoring and evaluation processes

Materials

- Copies of the handouts

- Flipchart paper

- Masking tape

- Markers

- Post-it notes or index cards in several colors

- Small "dot" stickers in several colors

- Laptop computer

- Projector

- Screen

Overview (2.5-3 hours)

Introduction/Ground Rules/Icebreaker (20 minutes)

Objectives and topics (5 minutes)

Key terms (5 minutes)

Exercise: what is monitoring and evaluation (10 minutes)

Why is M&E important? (10 minutes)

Gender and M&E (15 minutes)

Logical framework (15 minutes)

Exercise: Logframe race (10 minutes)

Indicators, baselines, and benchmarks (10 minutes)

Project life cycle (10 minutes)

Data collection and analysis (10 minutes)

Exercise: Integrating gender (30 minutes)

Evaluation design (10 minutes)

Conclusion/Questions/Evaluation (15 minutes)

Trainer’s Note:

This presentation provides a broad overview of monitoring and evaluation (M&E) and how gender can be mainstreamed into these processes. It covers the importance of M&E and why projects that fail to address gender issues are more likely to fail or to exacerbate existing inequalities. The presentation also provides insight into how to design projects using a logical framework approach and how to design indicators that are gender sensitive. It covers the M&E project life cycle and poses a series of questions that one can ask to determine whether gender has been mainstreamed in a project. It provides advice on data collection and analysis and how to design an evaluation. For participants who would benefit from more in-depth exposure to M&E, consider including the presentation on M&E tools.

When introducing this module, keep in mind the following:

- Encourage participants to be active.

- The course is designed to increase and enhance the knowledge and skills of each participant.

- Keep realistic expectations. This session is an introduction to monitoring and evaluation. Adjust your expectations depending on the level of experience your participants have with this topic.

- Always consider the experience your participants are bringing to the table. Even where it is not noted in the Trainer Note, feel free to draw on their knowledge and ask them to share their experiences.

Please adapt the PowerPoint presentation, exercises, examples and handouts in advance of your workshop. They have been created for a global audience and need to be adapted to better suit the local context, the background of your participants and their level of experience. Terms, images and examples from the participants’ country or region should be used as much as possible so that they are relevant and contextually appropriate.

This Trainer's Guide is meant to serve as a companion resource to the associated PowerPoint presentation. The vast majority of the information you will need is included in the notes section of each presentation. Additional instruction on how to facilitate some of the exercises and information that would not fit in the slide notes has been included here. As such, this Guide is not meant to be a stand-alone resource but rather a complement to the presentation.

If this is the first presentation in your workshop, start with participant introductions and ground rules prior to launching into the content of the session. You may also want to start with an icebreaker activity to get participants more acquainted and comfortable with you and each other. You may wish to ask participants to share their expectations for what they will get out of the training workshop. Understanding their expectations will allow you to further tailor your presentations, as possible, and to help relate the objectives of the sessions to the interests of the participants.

Trainer’s Note: Key Terms (slide 5)

Ask the participants to define the terms first and then decide on a common definition based on their responses and the definitions below. What do these terms mean in the context of the lives and work of the participants?

You might also ask them to suggest other terms relating to monitoring and evaluation that they think need to be defined at the onset. You should let them know that they are welcome to stop and ask for clarification at any point during the session if there is a term with which they are unfamiliar or one which they believe requires further discussion.

- Indicator: A thing, especially a trend or fact that indicates the state or level of something. Indicators can be quantitative (measuring the quantity of something) or qualitative (assessing the quality of something).

- Input: The human, material, and financial resources that you put into your project to produce the outputs. For a training program for women political activists, the inputs might be trainers, staff, time, and money.

- Output: These are the “deliverables” - products and/or services generated by a project. What is produced as a result of the inputs invested in a project. For a training program for women political activists, the outputs might be a training workshop and a training manual.

- Intermediate result (IR): These are the results of project activities that precede and lead to the achievement of longer-term objectives. How can you carry on the example started under “output”. What would an IR be here? Identification of women political activists? Better relationship with political party leaders?

- Outcome: The result of an action or process. More specifically, the result attained after implementing the project. Continuing the example, could an outcome be more women in decision-making roles in the political parties? Or more women candidates?

- Objective: A thing aimed at or sought. The effect of intermediate results on the target or beneficiaries by the end of the project. Objectives support the attainment of the goal. What you intend to accomplish by the end of the project. The objective of a training program for women political activists might be to enhance the capacity of women to run effective election campaigns.

- Goal: Long term, widespread improvement in society beyond the life of the project. The goal of a training program for women political activists might be to increase the number of women serving in elected office.

- Target: A target indicates the number, timing and location of what is to be achieved. For example, a target for the Millennium Development Goal of eradicating extreme poverty is to halve the proportion of people living on less than a dollar a day by 2015. If your objective is to enhance the capacity of women to run effective campaigns, your target may be to train 50 women by the end of the program or to conduct 15 training workshops in four regions.

- Baseline: A starting point from which a comparison can be made and performance of a project can be measured. The situation before the project begins. For example, if the goal of the project is to increase the number of women in elected office, you would want to establish the baseline before the project started – that only four percent of local councilors in Country X were women.

- Impact: According to the United Nations, impact is the “overall effect of accomplishing specific results. In some situations it comprises changes, whether planned or unplanned, positive or negative, direct or indirect, primary and secondary that a project helped to bring about. Impact is the longer-term or ultimate effect attributable to a project.

- Gender: Gender refers to the socially determined differences between women and men that are learned, changeable over time and have wide variations both within and between cultures. Gender is related to how we are perceived and expected to think and act as women and men because of the way society is organised not because of our biological differences. People are born female or male, but learn to be girls and boys who grow into women and men. They are taught the ‘appropriate’ behaviour and attitudes, roles and activities, and how they should relate to other people. This learned behaviour is what makes up gender identity, and determines gender roles.

Additional Resources

- World Bank Institute Gender and Development Trainer's Manual

This online resource includes a module on monitoring and evaluation that covers basis concepts as well as provides guidance on how to incorporate gender into the process. It includes learning cases that could be incorporated into your workshop.

- Integrating Human Rights and Gender Equality in Evaluation: Towards UNEG Guidance

This manual by the United Nations Evaluation Group (UNEG) provides helpful insight into how to mainstream gender into evaluations. It includes sections on integrating gender into evaluation design, terms of reference, and into the evaluation, itself. It also includes a checklist which can be used to verify whether gender was considered at each step of the process. The document is available in Arabic, English, French and Spanish.

- Security Sector Reform Assessment, Monitoring, Evaluation and Gender

This guide developed by United Nations International Research and Training Institute for the Advancement of Women, while specific to security sector reform, provides useful information on monitoring and evaluation, in general, and outlines specific steps that can be taken to integrate gender throughout the process. It is available in Arabic, English, French, Indonesian, Montenegrin and Russian.